## Sheet1
Serial No. | Contract Number | Contract Description | Procurement Category | Cost Estimate (US$ Million) | Procurement Method | Particular Selection Method | Bank's Prior Review | Scheduled Date of Publication of REOI/SPN | Contract Duration - months | Advance Procurement | Retroactive Financing
A. Consulting Services
1 | CONSU-001 | Technical, environmental and social supervision | Consulting services | 800000 | National Competitive Selection(NCS) | QCBS | Yes | T 1 - 2026 | 60
2 | CONSU-002 | Communication | Consulting services | 600000 | National Competitive Selection(NCS) | QCBS | Yes | T 1 - 2026 | 60
3 | CONSU-003 | Financial | Consulting services | 600000 | National Competitive Selection(NCS) | QCBS | Yes | T 1 - 2026 | 60
4 | CONSU-004 | Studies (Plans) and Projects - Vias Urbanas | Consulting services | 500000 | National Competitive Selection(NCS) | QCBS | Yes | T 1 - 2026 | 36
5 | CONSU-005 | Socio-Environmental Study | Consulting services | 13000 | Direct Selection | QCBS | Yes |  | 2 | Yes | Yes
6 | CONSU-006 | Studies (Plans) and Projects - Parques e Praças | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
7 | CONSU-007 | Studies (Plans) and Projects - Casas de bombas | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
8 | CONSU-008 | Program Management | Consulting services | 300000 | National Competitive Selection (NCS) | CQS or QCBS | No | T 1 - 2026 | 60
9 | CONSU-009 | External Audit | Consulting services | 100000 | National Cometitive Selection/direct selection |  | Yes | T 1 - 2027 | 48
10 | CONSU-010 | Impact Studies, Climate Change and Hydrological | Consulting services | 700000 | National Competitive Selection(NCS) | QCBS | Yes | T 2 - 2026 | 36
11 | CONSU-011 | Risk Management Training Program | Consulting services | 100000 | National Competitive Selection or Direct contracting |  | No | T 2 - 2026 | 24
12 | CONSU-012 | Studies (Plans) and Projects -Intervenções viárias (viaduto) | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
13 | CONSU-013 | Studies (Plans) and Projects -Arroio Passinhos | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
14 | CONSU-014 | Studies (Plans) and Projects Events center | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
15 | CONSU-015 | Studies (Plans) and Projects Masterplans | Consulting services | 500000 | Competition (National System) | QCBS | Yes | T 1 - 2026 | 36
| Subtotal A |  |  | 6713000
B. Goods, Works and non-Consulting Services
12 | WORKS-001 | Restoration of Urban Infrastructure in the Meu Rincão region | Works | 2000000 | National Competiive Tendering (NCT) |  | No | T - 2 - 2026 | 48
13 | WORKS-002 | Urban Infrastructure Restoration Carlos Wilkens | Works | 1500000 | National Competiive Tendering (NCT) |  | No | T 3 - 2026 | 48
14 | WORKS-003 | Restoration of Urban Infrastructure Vila Eunice | Works | 1500000 | National Competiive Tendering (NCT) |  | No | T 3 - 2026 | 48
15 | WORKS-004 | Restoration of Urban Infrastructure in Parque da Matriz | Works | 1500000 | National Competiive Tendering (NCT) |  | No | T 1 - 2026 | 48
16 | WORKS-005 | Rehabilitation of General Flores da Cunha Avenue | Works | 3500000 | National Competiive Tendering (NCT) |  | No | T 1 - 2027 | 12
17 | WORKS-006 | Requalification and construction of squares and parks: | Works | 12500000 | National Competiive Tendering (NCT) |  | Yes | T 2 - 2026 | 60
18 | WORKS-007 | Pumping houses | Works | 2500000 | National Competiive Tendering (NCT) |  | No | T 2 - 2026 | 48
19 | WORKS-008 | Urbanization of the Passinhos Stream | Works | 3000000 | National Competiive Tendering (NCT) |  | No | T 1 - 2027 | 48
20 | WORKS-009 | Execution of the Drainage and Flood Containment Plan | Works | 7000000 | National Competiive Tendering (NCT) |  | Yes | T 1 2027 | 48
21 | WORKS-010 | Resilient road works - Av. Fernando Ferrari | Works | 15000000 | National Competiive Tendering (NCT) |  | Yes | T 3 - 2026 | 60
22 | WORKS-011 | Resilient road works - Route "close" to RS 010 | Works | 10000000 | National Competiive Tendering (NCT) |  | Yes | T 3 - 2026 | 60
23 | WORKS-012 | Interventions at the intersection of Av. Fernando Ferrari with Av. Gen. Flores da Cunha | Works | 7000000 | National Competiive Tendering (NCT) |  | Yes | T 1 - 2028 | 36
24 | WORKS-013 | CCDCED and Administrative Center | Works | 8000000 | National Competiive Tendering (NCT) |  | Yes | T 1 - 2027 | 48
25 | WORKS-014 | Emergency and Events Center | Works | 3000000 | National Competiive Tendering (NCT) |  | No | T 1 - 2027 | 48
26 | GOODS-001 | Flood Monitoring System | Goods | 750000 | National Competiive Tendering (NCT) |  | No | T 2 - 2026 | 48
27 | GOODS-002 | Geographic Information System (GIS) | Goods | 2700000 | National Competiive Tendering (NCT) |  | No | T 1 - 2026 | 60