## 采购计划
Procurement Plan for Yunnan Kunming Changshui Airport Expansion and Green Development Project
S/N | Contract No. | Contract Name | Project Implementing Agency | Cost estimate |  | Source of fund |  | Procurement category | Procurement methods | Bank review method | Planned announcement date (DD/MM/YY) | Planned date of award (DD/MM/YY) | Contract period (Unit: month) | Amount of retroactive loan(Unit: Million USD) | Remarks
|  |  |  | RMB (Unit:Million) | USD (6.9RMB/1USD) (Unit:Million) | AIIB loans | Domestic supporting funds
1 | 0723-246000290003 | Works Around T2 - Underpass Works in the Northeast | YAG | 265.113 | 38.4222 | 80% | 20% | Works | NCT | Prior review | 15/12/2025 | 01/03/2026 | 40 | /
2 | 0723-246000290011 | Works Around T2 - Underpass Works in the Northwest | YAG | 444.5074 | 64.4214 | 80% | 20% | Works | IOCT | Prior review | 01/12/2025 | 01/03/2026 | 40 | /
3 | 0723-246000290004 | Works Around T2 - Apron Navigational Lighting and Power Supply and Distribution Works | YAG | 530.9029 | 76.9424 | 80% | 20% | Works | IOCT | Prior review | 01/04/2027 | 30/06/2027 | 12 | /
4 | 0723-246000290005 | Works Around T2 - East Part of Aerodrome Works in the Central Apron Area | YAG | 600 | 86.9565 | 80% | 20% | Works | IOCT | Prior review | 01/05/2027 | 31/07/2027 | 12 | /
5 | 0723-246000290006 | Works Around T2 - West Part of Aerodrome Works in the Central Apron Area | YAG | 641.0712 | 92.9089 | 80% | 20% | Works | IOCT | Prior review | 01/06/2027 | 31/08/2027 | 12 | /
6 | GXTC-A1-23290116 | Green Airport - New Energy Vehicles | YAG | 158.158 | 22.9214 | 100% | 0% | Goods | IOCT | Prior Review | 01/02/2028 | 30/04/2028 | 6 | /
7 | GXTC-A1-23290117 | Green Airport - Aircraft Ground AC Works | YAG | 51.1991 | 7.4202 | 100% | 0% | Goods | NCT | Prior Review | 01/10/2027 | 31/12/2027 | 10 | /
8 | GXTC-A1-23290118 | Green Airport - 400hz Power | YAG | 84.35 | 12.2246 | 100% | 0% | Goods | IOCT | Prior Review | 01/10/2027 | 31/12/2027 | 10 | /
9 | GXTC-A1-23290119 | Green Airport - Charging Pile | YAG | 71.31 | 10.3348 | 100% | 0% | Goods | IOCT | Prior Review | 01/10/2027 | 31/12/2027 | 10 | /
10 | GXTC-A1-23290120 | Green Airport - Noise Monitoring System | YAG | 14 | 2.029 | 100% | 0% | Goods | NCT | Post-review | 01/10/2027 | 31/12/2027 | 10 | /
11 | 0723-246000290008 | Soft Components | YAG | 61.55 | 8.9203 | 100% | 0% | Consulting | IOCT + QCBS | Prior review | 01/10/2026 | 31/12/2026 |  | / | According to the needs of the project, it is possible to continue to subdivide the bid section and adjust the selection method