## Publication - PP
P000314 Bukhara Region Water Supply and Sewerage Project
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 08-02-2023
Project Sector: | Water | Approved PP Update No.: | Version 13
AIIB Loan (USD Million): | 385.12 | Bank's Approval Date of the PP Update: | 2025-12-08
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/22 | Construction and Reconstruction Works for the Water Supply System in the Peshku District of Bukhara Region | 8,334,640.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-01-2025 | 07-03-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/21 | Construction and Reconstruction Works for the Water Supply System in the Peshku District of Bukhara Region | 15,995,290.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-01-2025 | 07-03-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/10 | Construction Works for Sewerage Network in Romitan District of Bukhara Region | 16,075,140.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-15-2025 | 12-21-2025 | 720 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/0102 | Construction Works for Sewerage Network in Gijduvan District of Bukhara Region | 22,614,325.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-15-2025 | 12-21-2025 | 720 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/11 | Procurement of Design and Build of Ramitan Wastewater Treatment Plant | 13,500,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 09-12-2025 | 02-13-2026 | 1440 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/03 | Procurement of Design and Build of Gijduvan Wastewater Treatment Plant | 19,620,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 09-12-2025 | 01-04-2026 | 1440 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/12-01 | Procurement of Design and Build of Karaulbazar Wastewater Treatment Plant (WwTP) | 9,030,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 03-24-2025 | 07-30-2025 | 1462 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/11-14 | Construction and Reconstruction Works for Water Supply and Distribution in Jondor District of Bukhara Region | 21,027,434.51 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-04-2025 | 10-15-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/09 | Design and Build of Karakul WwTP and 2 years of O&M Assistance | 13,990,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 07-04-2025 | 11-22-2025 | 1462 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/06 | Design and Build of Alat WwTP and 2 years of O&M Assistance | 9,000,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 07-04-2025 | 10-25-2025 | 1462 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/07 | Construction Works for Sewerage Network in Karakul District of Bukhara Region | 23,760,240.31 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-07-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/04 | Construction Works for Sewerage Network in Alat District of Bukhara Region | 24,748,966.53 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-07-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/27 | Construction and Reconstruction Works for the Water Supply System in the Romitan District of Bukhara Region | 9,700,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 10-23-2024 | 04-14-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/26 | Construction and Reconstruction Works for the Water Supply System in the Romitan District of Bukhara Region | 8,600,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 10-23-2024 | 04-14-2025 | 730 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | №BWSP-W-S/RFB/13-29/01/04 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Equipment) | 1,240,000.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-26-2024 | 06-15-2024 | 28 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/01/03&05 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Equipment) | 504,500.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-26-2024 | 06-15-2024 | 28 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP/LCS/01 | Selection of Consulting Services for: Financial Audit of “Bukhara Region Water Supply and Sewerage Project (Phase 1)” for 2020, 2021, 2022, 2023, 2024 and 2025 fiscal years | 59,600.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | LCS(Least Cost Based Selection) |  | Prior |  | 10-01-2021 | 05-19-2022 | 1324 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-WS/Shop/13-29/01 | Dredger for cleaning the bottom of sedimentation pond from sedimentary sludge | 50,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Prior |  |  | 05-24-2024 | 100 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/03 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 3- Emergency Vehicle, Mobile Laboratory and Leakage Detector) | 3,713,446.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 07-06-2024 | 365 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/02 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 2 - Equipment) | 1,030,107.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 07-06-2024 | 243 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/01/01-05 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Vehicles) | 2,978,296.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 06-07-2024 | 304 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/20 | Construction and Reconstruction Works for Water Supply and Distribution in Karaulbazar District of Bukhara Region | 1,800,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-20-2023 | 01-08-2024 | 356 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-WS/QCBS/03 | Consulting services by assisting the Project Implementing Entity (PIE) in preparation of tender documentation, project management and construction | 5,200,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-31-2023 | 01-25-2024 | 0 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP/QCBS-S/02 | Selection of a consulting company for the development of detailed design and estimate documentation for construction works by sewerage system | 6,200,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-24-2023 | 01-18-2024 | 14 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/QCBS/01 | Selection of a consulting company for the development of detailed design and estimate documentation for construction works by water supply system | 12,600,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-16-2023 | 01-10-2024 | 14 | Cleared
|  | Total: | 251,371,985.35