## Procurement Plan
Procurement Plan for Yunnan Kunming Changshui Airport Expansion and Green Development Project
2026-07-06
V11
No. | Contract No. | Contract | Project implemented by | Cost estimate |  | Source of funds |  | Procurement | Procurement method | Bank review method | Planned announcement date | Planned date of award | Contract duration (unit: month) | Retrospective loan amount (unit: USD 10,000)
|  |  |  | RMB 10,000 | USD 10,000 (RMB 6.9/USD 1) | AIIB loan | Domestic counterpart funds
1 | 0723-246000290013 | Works around T2 - Remaining Northeast and Northwest Underpass Works | Yunnan Airport Group Co., Ltd. | 35460.98 | 5139.2725 | 80% | 20% | Engineering | IOCT | Prior-review | 2026.9.10 | 2026.11.10 | 36 | /
2 | 0723-246000290004 | Works around T2 - East Part of Aerodrome Works in the Central Station Apron Area | Yunnan Airport Group Co., Ltd. | 60000 | 8695.6522 | 80% | 20% | Engineering | IOCT | Prior-review | 2026.9.30 | 2026.11.30 | 12 | /
3 | 0723-246000290005 | Works around T2 - West Part of Aerodrome Works in the Central Station Apron Area | Yunnan Airport Group Co., Ltd. | 64107.12 | 9290.887 | 80% | 20% | Engineering | IOCT | Prior-review | 2026.9.30 | 2026.11.30 | 12 | /
4 | 0723-246000290006 | Works around T2 - Navigational Lighting Works of the Central Station Apron Area | Yunnan Airport Group Co., Ltd. | 20657.19 | 2993.7957 | 80% | 20% | Engineering | NCT | Prior-review | 2026.9.30 | 2026.11.30 | 12 | /
5 | 0723-246000290013 | Works around T2 - Air Traffic Control Works of the Central Station Apron Area | Yunnan Airport Group Co., Ltd. | 32338.72 | 4686.771 | 80% | 20% | Engineering | IOCT | Prior-review | 2026.9.30 | 2026.11.30 | 12 | /
6 | GXTC-A1-23290116 | Green Airport - New Energy Vehicles | Yunnan Airport Group Co., Ltd. | 15815.8 | 2292.1449 | 100% | 0% | Goods | IOCT | Prior-review | 2026.08.01 | 2026.10.30 | 6 | /
7 | GXTC-A1-23290117 | Green Airport - Aircraft Ground AC Works | Yunnan Airport Group Co., Ltd. | 5119.9058 | 742.0153 | 100% | 0% | Goods | NCT | Prior-review | 2027.10.01 | 2027.12.31 | 10 | /
8 | GXTC-A1-23290118 | Green Airport - 400Hz Power Supply | Yunnan Airport Group Co., Ltd. | 8435 | 1222.4638 | 100% | 0% | Goods | IOCT | Prior-review | 2027.10.01 | 2027.12.31 | 10 | /
9 | GXTC-A1-23290119 | Green Airport - Charging Piles | Yunnan Airport Group Co., Ltd. | 7131 | 1033.4783 | 100% | 0% | Goods | IOCT | Prior-review | 2027.10.01 | 2027.12.31 | 10 | /
10 | GXTC-A1-23290120 | Green Airport - Noise Monitoring System | Yunnan Airport Group Co., Ltd. | 1400 | 202.8986 | 100% | 0% | Goods | NCT | Post-review | 2027.10.01 | 2027.12.31 | 10 | /
11 | 0723-246000290008 | Soft Components | Yunnan Airport Group Co., Ltd. | 6155 | 892.029 | 100% | 0% | Consulting | IOCT + QCBS | Prior-review | 2026.10.01 | 2026.12.31 |  | /
Total |  |  |  | 256620.7158 | 37191.4081