## Publication - PP Template
P000365 Mumbai Metro Line 5
Project Country: | India | Bank's Approval Date of the Initial Procurement Plan: | 06-29-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): | 200.00 | Bank's Approval Date of the PP Update: | 06-29-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Activity Status
Mumbai Metropolitan Region Development Authority | CA-242 | Automatic Fare Collection | 3860000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-14-2024 | 03-14-2024 | Cancelled
Mumbai Metropolitan Region Development Authority | CA-237 | Package-3 (Automatic Fare Collection) | 4360000 | 100 | Works | DC (Direct Contracting) |  | Lowest Evaluated Cost | Post | No |  | 06-01-2026 | Cleared
Mumbai Metropolitan Region Development Authority | CA-239 | Package- 2 (Power supply & Traction, Lifts & Escalators, E&M Station and E&M Depot) | 57120000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-18-2025 | 07-18-2025 | Cleared
Mumbai Metropolitan Region Development Authority | CA-241 | Package-1 (Rolling Stock (72+60 = 132 Nos), Signalling & Telecommunication (12.2+12.7 = 24.9 KM), Platform Screen Doors (7+9 = 16 Stations) and Depot M&P) | 263190000 | 52.63 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-06-2025 | 11-06-2025 | Cleared
|  | Total: | 324670000

## Sheet1 (hidden)
P000365 Mumbai Metro Line 5
Project Country: | India | Bank's Approval Date of the Initial Procurement Plan: | 06-29-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): | 200.00 | Bank's Approval Date of the PP Update: | 06-29-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Mumbai Metropolitan Region Development Authority | CA-242 | Automatic Fare Collection | 3860000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-14-2024 | 03-14-2024 | 1 | Cancelled
Mumbai Metropolitan Region Development Authority | CA-237 | Package-3 (Automatic Fare Collection) | 4360000 | 100 | Works | DC (Direct Contracting) |  | Lowest Evaluated Cost | Post | No |  | 06-01-2026 | 1 | Cleared
Mumbai Metropolitan Region Development Authority | CA-239 | Package- 2 (Power supply & Traction, Lifts & Escalators, E&M Station and E&M Depot) | 57120000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-18-2025 | 07-18-2025 | 1 | Cleared
Mumbai Metropolitan Region Development Authority | CA-241 | Package-1 (Rolling Stock (72+60 = 132 Nos), Signalling & Telecommunication (12.2+12.7 = 24.9 KM), Platform Screen Doors (7+9 = 16 Stations) and Depot M&P) | 263190000 | 52.63 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-06-2025 | 11-06-2025 | 1 | Cleared
|  | Total: | 324670000