## Publication - PP
S000668 Project Preparation for the Water Supply and Sanitation Universal Access Program
Project Country: | Kyrgyzstan | Bank's Approval Date of the Initial Procurement Plan: | 08-25-2025
Project Sector: | Water | Approved PP Update No.: | Version 4
AIIB Grant (USD Million): | 4 | Bank's Approval Date of the PP Update: | 10-16-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2026-6 | Environmental and Social Assessments assistant | 11250 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 401 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-7-DC | Procurement assistant | 19776 |  | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 06-30-2026 | 184 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-8 | Engineer assistant | 19776 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 09-08-2025 | 10-16-2025 | 441 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-7 | Procurement assistant | 19776 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 09-08-2025 | 10-16-2025 | 441 | Cancel-Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-DED-QCBS-2025-3 | Detailed engineering designs of Chui Issyk-Kul and Osh oblasts | 1034478 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 09-04-2025 | 01-29-2026 | 250 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-DED-QCBS-2025-2 | Detailed engineering designs of Chui Issyk-Kul and Osh oblasts | 1034478 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 09-04-2025 | 01-29-2026 | 250 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-DED-QCBS-2025-1 | Detailed engineering designs of Chui Issyk-Kul and Osh oblasts | 1032084 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 09-04-2025 | 01-29-2026 | 250 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-6 | Environmental and Social Assessments assistant | 18838 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 10-04-2025 | 447 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-5 | Information specialist/translator | 35644 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 10-04-2025 | 447 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-4 | Local M&E consultant | 29703 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 07-09-2026 | 08-14-2026 | 140 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-3 | Local Procurement consultant | 34159 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 09-30-2025 | 11-14-2025 | 412 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-2 | Local Engineer consultant | 35644 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 07-09-2026 | 08-15-2026 | 139 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-HO-IC-2025-1 | Team leader (Project coordinator) | 37520 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 09-30-2025 | 11-14-2025 | 412 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-IC-2025-6 | International engineer consultant for quality control | 253740 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 10-30-2025 | 12-14-2025 | 383 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-Audit-LCS-2025-5 | Auditing Service | 7000 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | LCS(Least Cost Based Selection) |  | Post |  | 10-30-2025 | 04-11-2026 | 260 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-IC-2025-4 | Preparation of the Operational Manual | 8911 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 09-30-2025 | 11-14-2025 | 413 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-IC-2025-3 | Environmental and social assessments | 37129 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 10-31-2025 | 12-15-2025 | 381 | Cleared
State Institution for Development of Drinking Water Supply and Wastewater Disposal (SIDDWSWD) under the Water Resources Service of the Ministry of Water Resources, Agriculture and Processing Industry of the Kyrgyz Republic | AIIB-BS-CQS-2025-2 | Baseline Survey | 150000 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Prior |  | 11-28-2025 | 01-26-2026 | 120 | Cleared
|  | Total: | 3819906