## Publication - PP
P000309 Obigarm-Nurobod Road Project - Long Bridge and Approaches
Project Country: | Tajikistan | Bank's Approval Date of the Initial Procurement Plan: | 10-15-2024
Project Sector: | Transport | Approved PP Update No.: | Version 4
AIIB Loan (USD Million): | 75.50 | Bank's Approval Date of the PP Update: | 09-09-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Project Implementation Unit for Roads Rehabilitation | NCS-04/1 | National Environmental Specialist | 37,500.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 08-29-2026 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-06 | Consulting Services for scoping study and skills needs assessment | 50,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 10-10-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-05 | Interpreter / Administrative Assistant | 52,800.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 01-28-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-04 | Environmental Specialist | 60,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 01-28-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-03 | Financial Specialist | 60,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 01-28-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-02 | National Bridge Engineer | 60,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 01-01-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | NC-01 | Project Manager | 96,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 01-07-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | IC-02 | International Bridge Specialist | 50,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 12-10-2024 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | IC-01 | Project Implementation Support Individual Consultant | 114,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 12-10-2024 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | CS-03 | International Contract Specialist | 200,000.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 04-15-2025 | 05-23-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | CS-02 | Economic Empowerment for Women | 200,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 03-10-2025 | 07-22-2025 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | CS-01 | Construction Supervision Consultancy Service for Design, Build and Maintenance Civil Works Contract | 4,000,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 12-22-2023 | 05-17-2024 | 14 | Cleared
Project Implementation Unit for Roads Rehabilitation | CW-01 | Design, Build and Maintain Civil Works for Permanent High-level Long Bridge about 920 m long including the road approach works is 1.5 kilometers | 60,000,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | Yes | 11-14-2023 | 06-22-2024 | 28 | Cleared
|  | Total: | 64,980,300.00