## Publication - PP Template
P000705 Istanbul Seismic Mitigation and Emergency Preparedness Additional Financing Project
Project Country: | Türkiye | Bank's Approval Date of the Initial Procurement Plan: | 05-24-2024
Project Sector: | Urban | Approved PP Update No.: | Version 3
AIIB Loan (USD Million): | 165.00 | Bank's Approval Date of the PP Update: | 07-02-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Istanbul Project Coordination Unit | AF-AIIB-CD1 | Consultancy Services for Legal Advisor of ISMEP Project - 2026 | 44,166.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 02-03-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-GA4.1 | Procurement of 112 Emergency Prefabricated Stations for Istanbul Health Directorate (112 Emergency Ambulance Service) | 1,495,540.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-26-2024 | 09-25-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-11 | Reconstruction and Replenishment Works of Educational Facilities | 7,910,421.41 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 11-23-2024 | 01-23-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-10 | Reconstruction Works of Educational Facilities | 3,662,367.59 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-17-2024 | 06-17-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-08 | Retrofitting Works of Educational Facilities | 2,618,592.78 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 09-03-2024 | 11-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-07 | Retrofitting Works of Educational Facilities | 3,146,946.23 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 09-03-2024 | 11-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-06 | Retrofitting Works of Educational Facilities | 3,071,523.18 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 09-03-2024 | 11-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-CB3 | Consultancy Services for Design of Bakırköy Health Campus | 4,236,400.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 12-06-2024 | 05-02-2025 | 14 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-GA1.2 | Procurement of Software Development for Search and Rescue Unit | 45,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 03-15-2024 | 7 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-CB1 | Consultancy Services for Reconstruction Supervision of Educational Buildings | 4236400.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 07-11-2024 | 11-22-2024 | 14 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-CB2 | Consulting Services for Construction Supervision for Strengthening of Educational Buildings | 1,588,650.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 11-25-2023 | 04-07-2024 | 14 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-05 | Retrofitting Works of Educational Facilities | 1,990,324.51 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-31-2024 | 07-31-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-04 | Retrofitting Works of Educational Facilities | 1,988,414.73 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-31-2024 | 07-31-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-03 | Retrofitting Works of Educational Facilities | 2,794,286.05 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-31-2024 | 07-31-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB3-GUCL-ONAR-02 | Retrofitting Works of Educational Facilities | 1,387,541.70 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-02-2024 | 03-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIIB-WB3-GUCL-ONAR-01 | Retrofitting Works of Educational Facilities | 1,050,047.86 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-02-2024 | 03-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-09 | Reconstruction Works of Educational Facilities | 13,016,356.07 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-02-2024 | 03-03-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-08 | Reconstruction Works of Educational Facilities | 22,610,809.05 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-15-2024 | 03-16-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-07 | Reconstruction Works of Educational Facilities | 8,039,398.77 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 12-16-2023 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-06 | Reconstruction Works of Educational Facilities | 25,025,771.62 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 12-16-2023 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-YAPIM-05 | Reconstruction Works of Educational Facilities | 5,175,695.34 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 12-16-2023 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-WORKS-04 | Reconstruction Works of Educational Facilities | 13,244,916.46 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 12-30-2023 | 420 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-WORKS-03 | Reconstruction Works of Educational Facilities | 15,786,392.75 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 12-30-2023 | 420 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-WORKS-02 (Tender Cancelled) | Reconstruction Works of Educational Facilities (Tender was cancelled) | 0.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 01-14-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-WB4-WORKS-01 | Reconstruction Works of Educational Facilities (2 schools) | 10,245,452.40 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2023 | 01-14-2024 | 28 | Cleared
Istanbul Project Coordination Unit | AF-AIIB-GA1.1 | Procurement of Digital DMR Simulcast Trunk Wide Area Radio System for Istanbul Provincial Disaster And Emergency Management Directorate | 3,706,850.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-03-2024 | 09-03-2024 | 28 | Cleared
|  | Total: | 158,118,264.50